## Budget
Project Budget
J2J AI Consulting. Fictional consultant-fee example. Amounts in USD.
Remaining approved fees | 66000 |  | Billed / approved | 78%
Workstream | Original fees | Approved changes | Approved fees | Billed to date | Remaining fees
Architectural design | 80000 | 10000 | 90000 | 99000 | -9000
Interior design | 120000 | 15000 | 135000 | 90000 | 45000
Lighting design | 30000 | 0 | 30000 | 27000 | 3000
Landscape design | 45000 | 0 | 45000 | 18000 | 27000
Total | 275000 | 25000 | 300000 | 234000 | 66000
Negative remaining fees indicate billing above approved fees. Confirm scope and approvals.
Billing percentage does not measure work completed. Blue numbers are editable inputs.